## Makati AIS Bug Tracker
BUG TRACKER FOR THE MAKATI ACCOUNTING INFORMATION SYSTEM (AIS)
TICKET NO. | DATE REPORTED | STATUS | ENVIRONMENT | REPORTED BY | ASSIGNED TO | PRIORITY LEVEL | MODULE AND SUB MODULE(S) | USER LEVEL | ISSUE DESCRIPTION | DEVICE ¦ SCREEN SIZE ¦ BROWSER (Chrome ¦ Mozilla ¦ Firefox) | PAGE LINK | FEEDBACKS/COMMENTS/REMARKS
1 | 2024-07-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Low | Bookkeeping > Journalization and DV > For Journalization | All Users | Add "Add entry" button for all transactions. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Ongoing fix.
2 | 2024-10-30 | Fix in Progress | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV | Processor | For journalization approval, the process is up to Sir Jemuel only. This applies to payments, payroll, and remittances. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | QA Tester Comment: As of 11/15/24: Remittances from payroll that were sent for jev does not reflect in the remittance transaction dashboard.
3 | 2024-10-30 | Fix in Progress | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV | Processor | For DV requires approval from Sir William. This applies to payments, payroll, and remittances. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | QA Tester Comment: As of 11/15/24: Remittances from payroll that were sent for jev does not reflect in the remittance transaction dashboard.
4 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV | All Users | Searching function (add name for searching). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
5 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV | All Users | Add jev number. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Ongoing fix.
6 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check and Other Online | Processor | When saving, a different dashboard appears. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
7 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check and Other Online | Processor | When selecting account number, a different dashboard appears. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
8 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check and Other Online | Processor | Can search in assigned check number but have prompt message. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Ongoing fix.
9 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | Once na is clicked all fields will be blank. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
10 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | If + is clicked (goes to white screen). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
11 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | Once N/A is selected the percent and amount should be cleared. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
12 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | DV viewing (Amount in words). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
13 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | Assigning of DV no. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
14 | 2024-11-15 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | Once done in DV goes to outgoing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Ongoing fix.
15 | 2024-11-15 | For QA Testing | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check Number Registry | All Users | Text wrap in Check Register. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
16 | 2024-11-15 | For QA Testing | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check Number Registry | All Users | Arrangement (registered, used, cancelled, not use) in check registry. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
17 | 2024-11-15 | For QA Testing | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check Number Registry | All Users | Check number registry (registered, used, cancelled, not use). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
18 | 2024-11-15 | For QA Testing | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check Number Registry | All Users | Add eye icon to view all added series (remove date outside but still inside add total of registered, used, cancelled, not use). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
19 | 2024-11-15 | For QA Testing | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > Check Number Registry | All Users | Action history not working. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | To test later, waiting for the Update in staging.
20 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > Payroll Transaction | All Users | Check Payroll Process flow. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
21 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | Adjust the columns and spacing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
22 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | Indent if credit. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
23 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | Total in word (text wrap). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
24 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | Amount due (text wrap). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
25 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | Print layout should not be cut off. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
26 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | Responsibility Center (OFFICE CODE). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
27 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | CAFOA No. If multiple, place 'see below' and then include it in the particulars. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
28 | 2024-10-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For DV | All Users | TIN, address (for payee). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
29 | 2024-10-30 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For Journalization | All Users | Put processor lower left. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
30 | 2024-10-30 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For Journalization | All Users | Date based on check or ada date (payment, payroll and remittances). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
31 | 2024-10-30 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For Journalization | All Users | Date based on income date of RCD. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
32 | 2024-10-30 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Bookkeeping > Journalization and DV > For Journalization | All Users | Others based on the date adjusted (but default date is current date). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
33 | 2024-10-30 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV | Processor | Data Entry for adjustment and cancellation (previous - this - total). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/7/24.
34 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > For DV | All Users | Add subtotal and line below value. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
35 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > For DV | All Users | BIR due to instead of word GMT, EWT etc. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
36 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > For DV | All Users | Add percentage of the BIR tax. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
37 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > For DV | Processor | Certified correct D. Add Php (amount) (,Net) after phrase. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
38 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > For DV | Processor | Add another column after billing adjustment for percentage. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
39 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > All Sub Modules > For DV | Processor | After saving add prompt message "Are you sure you want to save?" (Also in approval and review). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
40 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | It should not show if the billing and adjusted sections are null. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
41 | 2024-11-08 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Journalization and DV > For DV | Processor | Add the sum of the adjust. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
42 | 2024-11-12 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > For DV | All Users | Add filter (fund source). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
43 | 2024-11-12 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Check and Online Payment > For DV | All Users | Fix the routes of the navbar. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/13/24.
44 | 2024-12-15 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Bookkeeping > Settings | All Users | Source Fund and Target Fund (General Fund Proper). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Done in staging 11/15/24.
45 | 2024-07-15 | Need Info | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Low | Bookkeeping > Journalization and DV / Check and Online Payment | All Users | Add revert button (new feature). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Dev Comment: Already made the UX for this, but need more info regarding to the process of revert button.
46 | 2024-11-08 | Need Info | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV | Processor | User here must be the one to show on A auto. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Need more information from client.
47 | 2024-11-11 | Need Info | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | High | Bookkeeping > Journalization and DV > For DV | Processor | Certified correct A can add multiple when choosing attached files. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Need more information from client.
48 | 2024-10-22 | Not a Bug | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Low | Bookkeeping > Journalization and DV > For DV | Processor | Add tax selection. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Bookkeeping | Dev Comment: All goods. Not a bug.
49 | 2024-10-21 | Fix in Progress | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Budget Management > Executive Funds > List of Ongoing Allotment | All Users | Dates are not in chronological order. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Ongoing fix.
50 | 2024-11-05 | Fix in Progress | Production | Client | Menard Alcantara Chezter Custodio Kenneth Roy Vinoya | Normal | Budget Management > Executive Funds > List of appropriation for review/approval | Reviewer | The type of adjustment and the attached files in the update appropriation are not visible to the reviewer. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Ongoing fix.
51 | 2024-11-05 | Fix in Progress | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Budget Management > Executive Funds > Reports > SBU | All Users | Wrong data (all department). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | QA Tester Comment: still have incorrect value.
52 | 2024-09-26 | Fixed in Staging | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Budget Management > Executive Funds | Division Head | When approving a transaction, it takes 7x or more for it to be approved. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done in staging 11/13/24.
53 | 2024-11-04 | Fixed in Staging | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Budget Management > Executive Funds > Obligation > Obligation For Process | Processor | Balance Allotment are missing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done in staging 11/11/24.
54 | 2024-11-05 | Fixed in Staging | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Budget Management > Executive Funds | Processor | Other processors can see the tasks assigned to different processors. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done in staging 11/13/24.
55 | 2024-11-05 | Fixed in Staging | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive Funds > Obligation > Obligation For Process | Processor | Need to double-click when entering the current amount. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done in staging 11/11/24.
56 | 2024-11-18 | Fixed in Staging | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive Funds > Obligation > Obligation For Process | Processor | Processor can't save transactions. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done in staging 11/18/24.
57 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | Dashboard UDD scenario (When updating appropriation, the whole appropriation is missing) so the value is changing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done. To test later, waiting for the Update in staging.
58 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | Initial appro and allotment cannot change when adjusting transaction (Add initial and adjusted amount). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | QA Tester Comment: Initial appro and allotment cannot change when adjusting transaction (Add initial and adjusted amount).
59 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | Display "Type of Adjustment". | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | QA Tester Comment: Add Display "Type of Adjustment".
60 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | Processor | Edit "E" Allotment, viewing is not same with the process add and deduct is missing (processor). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | QA Tester Comment: Edit "E" Allotment, viewing is not same with the process add and deduct is missing (processor) - When clicking arrow down button for encoding of activity name, the page gets blank.
61 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | For Assignment pagination not aligned to selected number of page. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done. To test later, waiting for the Update in staging.
62 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | Edit "E" Obligation, changing of project or activity for certain transaction. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done. To test later, waiting for the Update in staging.
63 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | For Budget Adjustment missing transaction from PCICM. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done. To test later, waiting for the Update in staging.
64 | 2024-09-06 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive funds | All Users | Update Obligations must not be the same as the New Obligations (filtering). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Done. To test later, waiting for the Update in staging.
65 | 2024-11-05 | For QA Testing | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Budget Management > Executive Funds > Reports > SPPAI | All Users | Some programs where missing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | To test later, waiting for the Update in staging.
66 | 2024-08-13 | Need Info | Production | Client | Menard Alcantara Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Budget Management > Executive Funds > Approved Transactions | City Accountant | City Accountant can edit all information even when approved. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | QA Tester Comment: Can't save edited approved transactions.Network shows: error: "Call to a member function update() on null" message: "something went wrong"
67 | 2024-06-14 | Need Info | Production | Client | Menard Alcantara Chezter Custodio Kenneth Roy Vinoya | Low | Budget Management > Executive Funds | Processor | Add new item then put modal then add necessary details if any. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Need more information from client.
68 | 2024-07-15 | Open Task | Production | Client | Menard Alcantara Chezter Custodio Kenneth Roy Vinoya | Low | Budget Management > Executive Funds | All Users | Add revert button (new feature). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/Budget-Management | Need more information from client.
69 | 2024-07-05 | Can't Reproduce | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Normal | Document Management > Incoming | Processor | Bearer Information should be smart search based on Payee. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Set the ticket to not a bug by the dev.
70 | 2024-10-08 | Can't Reproduce | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Low | Document Management > Incoming > Communications | Division Head | Can edit addresee. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Set the ticket to not a bug by the dev.
71 | 2024-09-02 | Fix in Progress | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Normal | Document Management > Incoming > Previous Transactions | Processor | Redo Previous Transaction. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Ongoing fix.
72 | 2024-09-06 | Fix in Progress | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | High | Document Management > Outgoing | Processor | After selecting and generating transmittal no., transaction will go to 'Awaiting for Transmittal' then enter transmittal details then save then transaction will go to report. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | QA Tester Comment: Bugs as of 10/16/24 10:10AM CONTRACTS/PO: In the "awaiting for transmittal" tab. When entering the transmittal details and saving it, an error appeared ('something went wrong'), and then the transaction disappeared from the dashboard when I refreshed it. PRE AUDIT: In the "awaiting for transmittal" tab. When entering the transmittal details and saving it, an error appeared ('something went wrong'), and then the transaction disappeared from the dashboard when I refreshed it. PAYMENT: Can't generate transmittal number (transaction is not reflecting to the awaiting for transmittal tab) PAYROLL: For outgoing tab: It's stuck on 'Are you sure you want to save this transaction?' even when I click yes. (The transaction reflects to awaiting for transmittal tab when I close it.) Awaiting for transmittal tab: the 'Enter transmittal details' button is not functioning.
73 | 2024-09-06 | Fix in Progress | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Document Management > Incoming / Outgoing / Reports | Division Head | No view button when clicking "D" button. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | QA Tester Comment: Bugs as of 10/15/24 2:39PM OUTGOING: BOT: The dashboard of the D button gets stuck on loading when the viewed document is closed (Both for outgoing and awaiting transmittal tab) PAYMENT: The D button is not working. The dashboard for the D button only appears when switching to another tab (Both for outgoing and awaiting transmittal tab). PAYROLL: 'D' Button not Functioning (both for outgoing and awaitting for transmittal tab). COMMUNICATIONS: Can't view document using processor account (all documents uploaded by Radam, Jasmin) REPORTS: CHECK TRANS: The D button is not working. The dashboard for the D button only appears when switching to another tab. LIQUIDATION OF CA: The dashboard of the D button gets stuck on loading when the viewed document is closed. OTHERS: The D button is not working. The dashboard for the D button only appears when switching to another tab.
74 | 2024-11-07 | Fixed in Staging | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Normal | Document Management > Incoming > Check Transactions | Processor | Details not reflecting. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Done in staging 11/14/24.
75 | 2024-04-05 | Not a Bug | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Normal | Document Management > Cancelled Transactions | All Users | This is to add another tab wherein it would be showing the transactions that were archived, deleted, or cancelled by the users. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Set the ticket to not a bug by the dev.
76 | 2024-10-08 | Not a Bug | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Normal | Document Management > Incoming > Contracts/PO | Processor | Add text fields for pr number (not mandatory). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Set the ticket to not a bug by the dev.
77 | 2024-10-08 | Not a Bug | Production | Client | Jose Mari Dalugdug Paulyn Placido Kenneth Roy Vinoya | Urgent | Document Management > Incoming > Print Receiving Receipt | All Users | When a transaction was ticked, then searched for a transaction and also tick that transaction, the ticked box should be included with the newly ticked box in printing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Set the ticket to not a bug by the dev.
78 | 2024-09-06 | Open Task | Production | Client | Jose Mari Dalugdug Kenneth Roy Vinoya | Urgent | Document Management > Incoming > Contracts/PO / Payment Transactions | Processor | Upload document function for contracts and payment transaction | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/document | Not Started yet.
79 | 2024-10-29 | Fix in Progress | Production | Client | Menard Alcantara Paulyn Placido Kenneth Roy Vinoya | Normal | Payroll and Remittances Management > New payroll > Payroll Data Entry | Reviewer | Grand Total data incomplete. There's no subtotal in the grand total. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | QA Tester Comment: Miscalculation in netpay grand total.
80 | 2024-07-10 | Need Info | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Low | Payroll and Remittanaces Management > Reports | All Users | Add dashboard in reports reflecting all processed payrolls based on assigned Transaction Number. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Need more information from client.
81 | 2024-07-15 | Need Info | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Low | Payroll and Remittances Management > New Payrolls | Processor | Add revert button (new feature). | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Need more information from client.
82 | 2024-07-10 | Not a Bug | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Low | Payroll and Remittances Management > New Payrolls > For Certification | Division Head | Add "enable/ disable" function in signatories since some payrolls requires 3 signatories only. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Set the ticket to not a bug by the dev.
83 | 2024-07-10 | Not a Bug | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Low | Payroll and Remittances Management > New Payrolls > For Certification | Division Head | The "CERTIFIED" portion in the signatories could be edited. (ex. Vice Mayor). | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Set the ticket to not a bug by the dev.
84 | 2024-07-31 | Not a Bug | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Low | Payroll and Remittances Management > New Payrolls > In Process | Division Head | Are all payrolls already uploaded and processed still affected if additional column is made in the payroll format? | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Dev Comment: Yes
85 | 2024-07-10 | Open Task | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Low | Payroll and Remittances Management > New Payrolls > For Certification | All Users | Correction on the alignment of signatories' name. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Not Started yet.
86 | 2024-09-06 | Open Task | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Urgent | Payroll and Remittanaces Management > Reports | All Users | Reports (Categorize). | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Not Started yet.
87 | 2024-09-06 | Open Task | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Urgent | Payroll and Remittanaces Management > New Payrolls / Processed Payrolls / Remittances / Employees Enrollment | Division Head | User can be assigned multiples times. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Not Started yet.
88 | 2024-09-07 | Open Task | Production | Client | Menard Alcantara Kenneth Roy Vinoya | Urgent | Payroll and Remittanaces Management > New Payrolls / Processed Payrolls / Remittances / Employees Enrollment | Division Head | Any Division Head enable "E" button to edit details. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | Not Started yet.
89 | 2024-09-08 | Return to Dev | Production | Client | Menard Alcantara Paulyn Placido Kenneth Roy Vinoya | Low | Payroll and Remittanaces Management > Processed Payrolls | Reviewer | Logo not appearing in print certification. | Desktop (Laptop) ¦ 100% ¦ Edge | testmyais.simplevia.com/payroll-and-remittances | QA Tester Comment: Logo still doesn't appear in print certification.
90 | 2024-11-05 | Fix in Progress | Production | Client | Chezter Custodio Alvin Nakpil Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Contracts/P.O. | All Users | Receiving Clerk -> Division Head (Assigning) -> Processor (Processing) -> Division Head (Approving) -> City Accountant (Approving then transaction will automatically send for budgetary adjustment) -> Budget Management (Budget process exec) -> Outgoing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | After approving using DH account, the transaction goes to processed tab instead of city accountant dashboard for budget adjustment.
91 | 2024-07-15 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > Payment Transactions | Processor | Add CAFOA under PCICM (like in payroll). The process would be when the data entry is selected and the E button is used, there should be a data entry for the CAFOA to be assigned to the data entry. This should be on Payment Transactions only. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/7/24.
92 | 2024-09-26 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > Contracts/P.O. > View Contracts | Processor | If a transaction has multiple stock/property rows, the print layout only displays the first row. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/18/24.
93 | 2024-10-29 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Processor | Can't send for jev even if there is no 'no' responses on the checklist. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/11/24.
94 | 2024-10-29 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > PreAudit Transactions / Payment Transactions > Action Slip | All Users | The amount in the action slip should have a comma. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
95 | 2024-10-29 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > PreAudit Transactions / Payment Transactions > Action Slip | All Users | The action slip remarks should not be a textbox since the box is only for printing. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
96 | 2024-10-29 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > PreAudit Transactions / Payment Transactions > Action Slip | Processor | There should no longer be an approve button, it should just be a save button for add entries. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
97 | 2024-10-29 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > PreAudit Transactions / Payment Transactions > Action Slip | Reviewer | The content of the action slip should not be removed unless the checklist in contract data entry is edited from 'no' to 'yes. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
98 | 2024-10-30 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > PreAudit Transactions / Payment Transactions | Processor | The PCICM processor prefers that the eye icon displays only the contract data entry, with a "View Action Slip" button included in the contract data entry section. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/18/24.
99 | 2024-11-05 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > Contracts/P.O. / PreAudit Transactions / Payment Transactions | Division Head | Add "In Process" Tab Arrrangement should be: For Assignment ¦¦ In Process ¦¦ For Approval ¦¦ Processed | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/7/24.
100 | 2024-11-05 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > Contracts/P.O. | Division Head | 'For Budget Adjustment' button is not disabled even when the transaction has already been sent for budget adjustment. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/11/24.
101 | 2024-11-08 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Low | Processing of Claims and Internal Control Management > Contracts/P.O. / PreAudit Transactions / Payment Transactions > For Assignment | Division Head | Arrange assignee alphabetically based on surname (capitalized). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/18/24.
102 | 2024-11-11 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Processor | Save button doesn't function. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
103 | 2024-11-11 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > Payment Transactions | Reviewer | Can't process transaction. 'R' Action button is disabled. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
104 | 2024-11-11 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | City Accountant | Can't process transactions because 'R' action button is disabled. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/14/24.
105 | 2024-11-13 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > PreAudit Transactions > For Assignment | Division Head | "In process" transaction also reflects in the "for assignment" dashboard. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/18/24.
106 | 2024-11-14 | Fixed in Staging | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Low | Processing of Claims and Internal Control Management > Payment Transactions | Reviewer Division Head City Accountant | Remarks in checklist eye icon is not reflecting. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done in staging 11/18/24.
107 | 2024-10-04 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > Payment Transactions | All Users | Processed Tab (Status not changing) but changes depending on where the transactions is. Ex. FOR JEV, FOR DV, etc. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Payment transaction sent for jev was not reflecting in bookkeeping.
108 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Processor | Processor: For Review (There should be a list of reviewers to choose) / For Approval (Either Sir Jo or Sir William) and For JEV. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Processor: For Approval List of approvers should be either sir jo or sir william. The send for approval button displays the list of reviewers.
109 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Reviewer | Reviewer: For Approval (Either Sir Jo or Sir William) and Send for JEV. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done. To test later, waiting for the Update in staging.
110 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Division Head | Division Head: For Approval (Default sir William) and For JEV. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done. To test later, waiting for the Update in staging.
111 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | City Accountant | City Accountant: When approved, it should automatically send for JEV. (There's no send for JEV button in CA account). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done. To test later, waiting for the Update in staging.
112 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | City Accountant | When there are findings and final approval is given, it should automatically go to 'For Outgoing.' The status should indicate 'Outgoing - With findings,' but the transaction should still be in the In process tab. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Can't test due to approved transactions from Division Head doesn't reflect in the City Accountant's Dashboard.
113 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | City Accountant | When there are no findings and Final approval is given, the status should be 'For JEV.' then the transaction will go in the Processed tab. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Can't test due to approved transactions from Division Head doesn't reflect in the City Accountant's Dashboard.
114 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Reviewer Division Head | Reviewer, and DH when there's no finding and was sent for approval, status should be: for the Reviewer: "For Approval - DH" while for the DH: "For Approval - CA" | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done. To test later, waiting for the Update in staging.
115 | 2024-10-29 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Urgent | Processing of Claims and Internal Control Management > Payment Transactions | Reviewer Division Head | Reviewer, and DH when there's a finding and was sent for approval, status should be: Both for Reviewer and DH: "For Approval - With Findings". | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Done. To test later, waiting for the Update in staging.
116 | 2024-11-11 | For QA Testing | Production | Client | Chezter Custodio Alvin Nakpil Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > Payment Transactions> Action History | All Users | Action history not updating when sending for JEV. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | To test later, waiting for the Update in staging.
117 | 2024-11-14 | For QA Testing | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | High | Processing of Claims and Internal Control Management > Payment Transactions | Processor | Can't send for jev using processor account. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Dev Comment: The transaction that was sent for JEV moved to bookkeeping bugs. To test later, waiting for the Update in staging.
118 | 2024-11-05 | Need Info | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > Contracts/P.O. / PreAudit Transactions / Payment Transactions | Division Head City Accountant | DH and CA should see all for Approval transactions. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | QA Tester Comment: As of 11/14/24: Transactions sent for approval by the DH are not appearing in the CA's Dashboard. It goes to the processed tab. Dev Comment: contract? preaud? payment?
119 | 2024-11-05 | Need Info | Production | Client | Chezter Custodio Paulyn Placido Kenneth Roy Vinoya | Normal | Processing of Claims and Internal Control Management > Contracts/P.O. / PreAudit Transactions / Payment Transactions | Division Head City Accountant | Add filtering for approval transactions where the approval is for CA or For DH. | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | QA Tester Comment: As of 11/14/24: Transactions sent for approval by the DH are not appearing in the CA's Dashboard. It goes to the processed tab. Dev Comment: contract? preaud? payment?
120 | 2024-07-15 | Open Task | Production | Client | Chezter Custodio Kenneth Roy Vinoya | Low | Processing of Claims and Internal Control Management > Contracts/P.O. / PreAudit Transactions / Payment Transactions | Processor | Add revert button (new feature). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/PCICM | Not Started yet.
121 | 2024-07-03 | Open Task | Production | Client | Menard Alcantara Chezter Custodio Jose Mari Dalugdug Alvin Nakpil Paulyn Placido Kenneth Roy Vinoya | Low | Admin Setting Management > Adding Multiple Divisions Per User | Division Head City Accountant | Add multiple division functionality assigning for users. (Ex. for processing, assigning should also include them on both modules. Currently only available on one user). | Desktop (Laptop) ¦ 100% ¦ Edge | https://testmyais.simplevia.com/admin | Not Started yet. Not priority.